## Accreditation Self-Evaluation 2024 Timeline

### Spring 2021/Fall 2021

|  |  |
| --- | --- |
| Events | Time  |
| Accreditation Faculty Co-Chair Announcement is sent out  | April 27, 2021 |
| Accreditation Faculty Co-Chair Announcement closes | May 7, 2021 |
| Appointment of Accreditation Faculty Co-Chair by College President | August 19, 2021 |
| Appointment of Standards Tri-chair Teams | August/September 2021 |
| Accreditation training by ACCJC | October 8, 2021 |
| Colleges to provide feedback on accreditation surveys (Employees and Students) | October 2021 |
| Accreditation Organizational Meetings | Nov/Dec 2021 |
| Accreditation District Coordination Meeting  | December 10, 2021 |
| District IRP to Administer Accreditation Survey-StudentsDistrict IRP to Administer Accreditation Survey-Employees | December 1-17, 2021Dec 14-Jan 21, 2022 |

### Spring 2022

|  |  |
| --- | --- |
| Events | Time  |
| Standards Leads collect evidence for the self-evaluation report  | January-May, 2022 |
| Kick-off meeting with tri-chairs (re: structure/timeline) \* Flex  | February 4, 2022 (2pm) |
| Accreditation survey results are available | March, 2022 |
| Incorporate accreditation survey results (if necessary) into standard narratives  | April, 2022 |
| Standard Tri-chairs turn in first round responses of self-evaluation report to Steering Committee for compilation | April 13, 2022 |
| **Accreditation Self-Evaluation Draft 1 distributed to College for feedback** | **April 29, 2022** |
| Standard IV.D Meeting with Board Subcommittee | Early May, 2022 |
| Public Forum Round 1 (PFR 1) | Week of May 9, 2022 |
| Feedback from Public Forum Round 1 (PFR 1) due | May 27, 2022 |

### Summer 2022

|  |  |
| --- | --- |
| Events | Time  |
| Incorporate changes and suggestions from (PFR 1) by Steering Committee  | June/July 2022 |

###

### Fall 2022

|  |  |
| --- | --- |
| Events | Time  |
| Standard Tri-chairs turn in second round responses of self-evaluation report to Steering Committee for compilation | (Noon) September 28, 2022 |
| **Accreditation Self-Evaluation Draft 2 distributed to College for feedback** | **October 14, 2022** |
| Public Forum Round 2 (PRF 2) | Week of October 31, 2022 |
| Feedback from Public Forum Round 2 (PFR 2) due | November 10, 2022 |
| Incorporate changes and suggestion from (PFR 2) by Steering Committee  | November/December 2022 |
| Start cataloging evidence for Self-Evaluation report (Draft 3) | October/December 2022 |
| Status Report to District Governance Council (DGC) and Chancellor Cabinet | December 7, 2022 |
| Status Report to Board of Trustees | December 15, 2022 |

###

### Spring 2023

|  |  |
| --- | --- |
| Events | Time  |
| Continue cataloging evidence for Self-Evaluation report (Draft 3) | January/February 2023 |
| Draft 3 feedback due to Steering Committee  | February 8, 2023 (noon)  |
| Incorporate changes and suggestions from Draft 3 by Steering Committee into Final Draft | February 2023 |
| **Distribute Draft 3 (Full Content)**  | **February 16, 2023** |
| All Constituency Approval -Academic Senate (2/28/23 & 3/14/2023) -Classified Senate (2/28/23 & 3/14/2023) -Associate Students (2/24/23 & 3/10/2021) | February/March, 2023 |
| Campus’ Approval of Self-Evaluation report  | April 4, 2023 |
| Add Final Edits, Cover Art, etc. | April, 2023 |
| **Send Final Draft to Vice Chancellor, Ed. Services for review and fact check** | **Week of April 17, 2023** |
| Send 4 print copies of “Final Draft” for Board Subcommittee (formatted) | May 1, 2023 |
| 1. Board Subcommittee review of the Final Draft
2. Chancellor Review of Final Draft
 | 2nd week of May |
| Chancellor’s Cabinet summary review of Self-Evaluation report | May 23, 2023 |
| District Governance Council (DGC) final review of Self-Evaluation report | June 8, 2023 |
| SDCCD Board approval of Self-Evaluation report | June 9, 2023 |

###

### Summer 2023

|  |  |
| --- | --- |
| Events | Time  |
| Final edits to ISER | June/July 2023 |
| Gather signatures | June/July 2023 |

###

### Fall 2023

|  |  |
| --- | --- |
| Events | Time  |
| **Send ISER to ACCJC** | **August 1, 2023** |
| Make arrangements for focused site visit  | September -November 2023 |

###

### Spring 2024

|  |  |
| --- | --- |
| Events | Time  |
| Make final arrangements for focused site visit  | January/February 2024 |
| Accreditation focused site team visit  | March 22, 2024 |